## Plan
ID	Work package	Target date	Risks / mitigations
1	a. Sourcing and aggregation of data sources for Named Entities of companies, people and places. / b. Download all Hansards as one dataset / c. Preparation of Hansard documents with NEs interpolated into the document using the NE lists aggregated above.	End April 2018	Data may not be available, or may be in unworkable formats. Use other/less data.
2	a. Perform manual validation of above Hansard documents to complete semi-automatic labelled data. / b. Construction of NER learning model BLSTM by constructing tensors; integration with and modification of https://github.com/0xnurl/keras_character_based_ner implementation.	End May 2018	Model may not perform the task
3	Familiarisation with Samtla SLM. Conversion of Hansard into correct format, and loading of Hansard data into Samtla.	Mid June 2018	Samtla SLM API may not be complete. Mitigation is for Dr Martyn Harris to load the corpus into the SML manually.
4	Familiarisation with Samtla back-end (Python Django) and integration of NER processing with departmental server.	End June 2018	Integration may not be possible due to unforeseen dependencies.
5	Familiarisation with Samtla front-end (Javascript jQuery) and integration of NER visualization.	End July 2018	Integration may not be possible due to unforeseen dependencies.
6	Evaluation of Samtla Char-NER system using k-fold cross-validation techniques. (train on only part of data)	End August 2018	Fall back to simpler evaluation methods; as a last-resort, crowd-source evaluation of Hansards enriched with NE data.
7	Finalise write-up into report	Before 17th Sept 2018

## Work Log
Date	WorkPackage	Aim	Issues	Resolutions	Extra content for Report
26/04/18	1a sourcing NEs	Worked on Kaggle NYC baby names	Names can be FN-LN or just FN. I guess we want to be able to detect both, as both occur in speech	Manually split all names up into FN, LN as well? Makes recognition more likely…	benefits of the pipeline approach – can iteratively improve each stage and only re-run downstream jobs
		DBPedia SPARQL got list of people	1.They’re in Unicode	To check with Martyn Harris
			2. They have profession names etc in brackets	Used foaf:name instead, fixed
			3. Tony Blair is a Person, but then so is Shadow_Cabinet_of_Tony_Blair	Post-processing validation?

		Post-processing of names	4.Duplicates not a problem – e.g. Ralph Allwood and Ralph Allwood, MBE – could both appear in a text. Entries like below ARE A problem:	TODO: remove start ad end brackets and quotes (without messing up unicode)
			(15 July 1914 – 8 November 1927)
			(1833-1905)

			5. Lots of Chinese, Russian and Arabic names – no principled reason to remove them, but it’s unlikely they would appear natively in Hansard
			6. biography-center.com no longer has names in easy parseable format	Scrap it – we have enough names from DBPedia
		Processed CONLL data	Reuters dataset not included
		SPARQL got list of companies	no issues
		SPARQL got list of places	no issues
07/07/18	Examine Keras	Correct typos
09/07/18	1a sourcing NEs	Remove double quotes from outputs, sanitise output dirs
	1b sourcing Hansards	Wrote multi-Hansard-Downloader using TWFY API which starts in 1919	serial download v slow before finding concurrent.futures – put comparative timings in report? Tried multiprocessing and infinite num of threads too
11/07/18	1b sourcing hansards	Today I found another API source for Hansard: https://api.parliament.uk/historic-hansard/	My scripts are written for https://www.theyworkforyou.com/api/, but this only goes back to 1919.
	1b preprocessing of Hansards	Downloaded raw hansards	They need HTML chars escaping in xml files	lxml etree
		Processed hansards	They need all markup lang tags removing	lxml etree
			bleach.clean failed to remove nested markup tags	lxml etree
			Used lxml etree which successfully removed all tags. But now speaker names are not shown, as they are only nested in the XML tags.	TODO find a way to preserve speaker names in the future.
			lxml etree does not like Unicode strings.	Had to force-encode string as utf-8 and the etree parser as utf-8 to fix
	2b	Try feeding Hansards into Keras model	Keras model is designed for max sent len of 200. If a debate is a sentence, max is 1.13m characters. We need to subdivide up the debates.	Add a new stage: file chunking. We ideally want to avoid chopping up an NE across 2 files…
			TextBlob struggles to segment accurately on sentence with ‘hon. Gentleman’.	TextBlob segmentation V SLOW, nltk was much faster
			NLTK still can’t cope with hon. Gentleman	Investigate https://stackoverflow.com/questions/34805790/how-to-avoid-nltks-sentence-tokenizer-spliting-on-abbreviations	Fixed using NLTK custom tokenizer
13/07/18	2b Integration with Keras	Try to integrate x with keras before solving interpolation (y) problem	Need to construct Numpy arrays with numerised alphabet. To do this, I need to get union of all characters used in the whole dataset	Create get_some_alphabet which just uses texts from the 1940s to construct alphabet. Hopefully we won’t have too many more characters since then.
				Use none-chunked Hansards as we still have same characters in them and it’s MUCH quicker.
				Save out alphabet object using Pickle
13/07/18	1c NE interpolation	Trying to interpolate such that words are turned into e.g. OOOO, but all whitespace and punctuation is preserved	word_tokenizer in NLTK only returns a list of words. To get spans of word start/ends, need to use a span_tokenizer which is not included in NLTK default tokenizer
		There’s a tension between work that’s easy to reason with (having each stage on disk), and work that’s efficient and processes quickly enough (skipping stages, delete as going along etc)
		String type immutable in Python	Trying inv hansard-interpolate-one hansard_gathering/chunked_hansard_data/1949-07-14/Oral\ Answers\ to\ Questions\ \&\#8212\;\ Electoral\ Register-chunk-388.txt cannot modify string. Either change to use concat, or a ctype as per https://stackoverflow.com/questions/10572624/mutable-strings-in-python	≈
17/07/18		Used string concat which works fine. Now can’t find any NEs as multi-word phrases are ignored by tokenizer.	Need to try multiple-word lookups in the NE files	word tokenizer in groups, or sliding n-grams?
18/07/18	1c NE interpolation	Fix tokenizing for interpolation – try NLTK ngrams		Keep working on hansard_gathering/chunked_hansard_data/1949-07-14/Oral Answers to Questions &#8212; Electoral Register-chunk-388.txt
				Solution was to use sliding windows over text spans, then for each window, try all suffixes from longest to shortest, in all the NE files	Examining I do recall that / Examining I do recall / Examining I do / Examining I / Examining do recall that Margaret / Examining do recall that / Examining do recall / Examining do / Examining recall that Margaret Thatcher / Examining recall that Margaret / Examining recall that / Examining recall / Examining that Margaret Thatcher was / Examining that Margaret Thatcher / Examining that Margaret / Examining that / Examining Margaret Thatcher was good / Examining Margaret Thatcher was / Examining Margaret Thatcher
	1b chunking	Need to process Hansards but have no disk	Not enough disk space on MAC	Back up raw hansards in tgz, then make processing algo delete raw hansards as it goes
		Interpolation throws up weird errors:
	1a	I have searched the International Monetary Fund rules, and I cannot find under which rule this is done.	I is an Org, The is a location, ‘.’ is a location…	Manual correction – remove ‘I’ from companies list ALL.txt. This came from DBPedia… Removed ‘.’ from locations and ‘the’
		2000000000000000111022222222222222222222222222200000010111020000000000000000000000000000000000000000001		Better resolution is to throw away words < 4 chars at processing stage, doing this now
	1b chunking	Starting chunk all	Chunking is very slow	Make chunking resumable by allowing date to be specified
		Interpolation works!		mattlap:~/bbk/masters_project mralph$ cat hansard_gathering/chunked_hansard_data/1929-12-23/Egypt.-chunk-1051.txt / It is sometimes said that it would be impossible, but I know there are experts who hold, on the contrary, that it would be a very strong position, and, indeed, actually stronger than a position based upon Cairo and Alexandria if Egypt were in revolt against our action.% mattlap:~/bbk/masters_project mralph$ cat hansard_gathering/interpolated_hansard_data/1929-12-23/Egypt.-chunk-1051.txt / 00000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000111111111100001111100000000000000000000000000000000000%
	2b Keras get x from texts	Need to translate chunked docs into numbered encodings	Don’t want to do padding in case sentence_maxlen changes	Decouple numerification from padding, do padding closer to keras-loading
		Cannot unpickle alphabet to encode debates into numbers	You can’t pickle in one module structure and unpickle in another. Have to wrap the keras char-based ner code into my module structure with __init__.py files
19/07/18	1c chunk	Run out of disk space	chunked sentences are too large	gzip in python
			Backup locations: raw on pen drive
			processed on dropbox
			Space blow out is caused by storing individual sentences in each file. Minimum file size is 4K – a lot of wasted space! Disk spin must have been limiting performance.	Get external drive and put different block size / filesystem on it	mattlap:~/bbk/masters_project/hansard_gathering/chunked_hansard_data/1965-07-22 mralph$ du -sh 'Security Commission (Report on Bossard and Allen Cases)-chunk-3511.txt.gz' / 4.0KSecurity Commission (Report on Bossard and Allen Cases)-chunk-3511.txt.gz / mattlap:~/bbk/masters_project/hansard_gathering/chunked_hansard_data/1965-07-22 mralph$ stat -f%z !$ / stat -f%z 'Security Commission (Report on Bossard and Allen Cases)-chunk-3511.txt.gz' / 218
				New idea: re-order pipeline so we interpolate directly from the processed data. Maybe we can chunk later, as we make sequences to feed into the model?
				Or maybe we chunk, but we just store the sentence offsets in their own file??
22/07/18	1c chunk	Method written to view file with sentence chunking based on a separate chunk spans file
	1a	Improve NE data hygiene before interpolating all Hansards
23/07/18	1a sourcing NEs	Split out job so I can just post-process NEs without re-downloading from SparQL-wiki	need to refactor, lots of repetition
		can’t remove brackets from start and end of NEs	They’re not standard ASCII brackets, need to find ALL brackets in Unicode		166 ( Institut catholique de Lyon ) / 167 ( Kanakpak Khemara Ponnakar ) / 168 ( Kommunistische Partei Deutschlands ) / 169 ( Le bureau national d'examen dentaire du Canada ) / 170 ( Mǎ Lái Xī Yà Fó Xué Yuàn ) / 171 ( Nasionale Konserwatiewe Party van Suid-Afrika) / 172 ( PT Media Nusantara Citra Televisi Indonesia) / 173 ( Pusat Pemantauan dan Pendedahan Maklumat Kebangsaan )
		extraneous quotes, whitespace, asterisks
	2a interpolation	NLTK 3.2 has bug for span_tokenize if it contains multiple quotation types	file_path = 'hansard_gathering/processed_hansard_data/1919-08-04/Oral Answers to Questions &#8212; Railway Materials in War Area..txt' / with open(file_path) as f: / ...: text: str = f.read() / ...: interpolated_text: str = "0" * len(text) / from datetime import datetime / ...: from nltk.tokenize import TreebankWordTokenizer / ...: from nltk import ngrams / ...: from typing import List / ...: import concurrent.futures / ...: import glob / ...: import itertools / ...: import os / ...: / tokenizer = TreebankWordTokenizer() / text_span_ngrams = ngrams(tokenizer.span_tokenize(text), n, pad_right=True)	Upgrade to NLTK 3.3 https://github.com/nltk/nltk/pull/2060
			results in
			--------------------------------------------------------------------------- / ValueError Traceback (most recent call last) / ~/bbk/masters_project/masters_venv/lib/python3.6/site-packages/nltk/tokenize/util.py in align_tokens(tokens, sentence) / 253 try: / --> 254 start = sentence.index(token, point) / 255 except ValueError: / ValueError: substring not found / During handling of the above exception, another exception occurred: / ValueError Traceback (most recent call last) / <ipython-input-36-01430904daf3> in <module>() / ----> 1 tokenizer.span_tokenize(half_text) / ~/bbk/masters_project/masters_venv/lib/python3.6/site-packages/nltk/tokenize/treebank.py in span_tokenize(self, text) / 177 tokens = raw_tokens / 178 / --> 179 return align_tokens(tokens, text) / 180 / 181 / ~/bbk/masters_project/masters_venv/lib/python3.6/site-packages/nltk/tokenize/util.py in align_tokens(tokens, sentence) / 254 start = sentence.index(token, point) / 255 except ValueError: / --> 256 raise ValueError('substring "{}" not found in "{}"'.format(token, sentence)) / 257 point = start + len(token) / 258 offsets.append((start, point)) / ValueError: substring "passed." not found in "
	2a interpolation	Interpolated a whole debate	Overlaps – if The House has been successfully interpolated as a Place, House, which is a company, overwrites the labels for the second half, leaving a dangling ‘The’	Change algorithm so that it checks if the current span is in the middle of an already-NE’d span, and skips it if so	def overlaps(ngram_span_window, recentest_match_end: int): / """ / See if the current span window already has a matched NE ending in it. / :param ngram_span_window: e.g.((0, 1), (2, 6), (7, 15), (16, 19)) / Note that because we pad_right, later elements in the tuple might be None, e.g.: / ((98, 102), (102, 103), None, None) / :param recentest_match_end: / :return: True if there would be an overlap / """ / ngrams = [x for x in ngram_span_window if x is not None] / return ngram_span_window[-1][-1] <= recentest_match_end
24/07/18	2a	Fixed overlap bug	Interpolation is too slow. It may be the python ‘in’ membership check	Replace list with set?	TODO compare list with set – speed improves hugely!!! From about 20 minutes to 5 seconds. How implemented?
			Still random places – e.g. ‘and the’ as a place, in SPARQL data	Remove all lines comprised of stop words?	A Dirty Data section?
25/07/18	2a interpolating	Fix datetime bug where month ignored	Was using %M not %m in datetime filter	corrected
	1a NE gathering	Need to remove stop-words from NE list	e.g. remove ‘and the’ as a place
		tech debt clean up	Allow all tasks to be invoked from tasks.py without shell
			Make all type checks pass
	2b preparation of x tensor	Need to determine some datasets	The model requires train, dev and test. Relative sizes? Can’t use date ranges or alphabetical division as that would bias the datasets. Need to hash all the data into 3 buckets of unequal sizes, such that it can be easily repeated in future.	Use last 2 parts of file path as entry into a hashing algorithm, e.g. “1972-07-20/Orders of the Day &#8212; Clause 211.txt”. Build up a list of which filenames are in which data set	Buckets have equal numbers of files: / Mattlap:~/bbk/masters_project/hansard_gathering/data_buckets mralph$ wc -l * / 8360 0.txt / 8414 1.txt / 8228 2.txt / 8322 3.txt / 8289 4.txt / 8071 5.txt / 8356 6.txt / 8419 7.txt / 66459 total
			accidentally overwrote hansard_gathering/processed_hansard_data/1948-07-13/Oral Answers to Questions &#8212; Prisoners of War (Repatriation).txt	Restore from backup
			Numerification is too slow. Doing lots of re-assignment of strings	Instead make a list of numbers, then join it as a last step	show change in 17d4716aadb8389d9aaf10a7a0d543e7ceda196e to numerify.py
	1c interpolation	Interpolation is the new bottleneck	We are re-assigning to string a lot to build the interpolated string	Can we make this faster by replacing the string re-assignment operations with a List, and stringify at the end? Done. Faster?
	2b tensor construction	Counted up total number of sentences (batch_size) for each dataset		As hoped for, train is half the dataset and dev/test are both half of it in size, more or less	mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat ALL_total_sentences_num / 182582013 / mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat train_total_sentences_num / 91294439 / mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat dev_total_sentences_num / 44985341 / mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat test_total_sentences_num / 46295292
27/07/18	2b tensor construction	It’s far too slow! Doing 0.01% takes about 20 minutes	Won’t have time to finish	Rehash across 320 buckets, then just try 1 bucket first to see if we can make a numpy array. Should go from 8000 debates per file to 200, 8 → 320 buckets is 40 times more
			Some debates have no sentences, indeed no content in them. Seems to be a problem with the API? For now, just skip over empty debates. CONFIRMED that the xmls only have tags in, no text
		Pickled an x batch	But it’s far too large – 4GB for 1/160 of the dataset. Must be because I’m padding all the sentences.	Could use char-based splitting not chunking? Might be faster anyhow… Would only need to change the span files, or right other ones of a more reasonable length	Trade-off – lots of data sparsity in padded arrays, or some interpolated data getting cut off at the word boundaries…
			Maybe 900 is just too long for sentences – try to find median length of sentences in the corpus	Wrote a script – median is 111. Having up’d original of 200 in keras repo to 900, I put it back to 200	4GB x_np file went down to 800 MB. We could fit the data into roughly 128GB. This suggests we’ll have to use get_x_y_generator to get it off the ground
		NEXT: write a create_y that uses span files to return the right interpolation ranges from a generator. This approach will inform a similar approach using another generator for get_x_y_generator
28/07/18	BAU	REFACTOR – remove one ‘matt.py’ package in the keras model
	2b	Alphabet get_texts tries to build alphabet off ALL the data	takes too long	Refactor to use the dataset hashing – only use contents of one bucket to set the alphabet. Alphabet is pretty consistent! This is also better distributed than just using a glob over one decade (previous approach) to get the alphabet characters
	2b	Force total_sentence_nums to be updated whenever we rebucket the data
29/07/18	2b	y tensor has wrong number of dimensions	I was building it to match the x tensor, but actually it needs to have one more dimension. Is the 3rd dimension of the y tensor a one-hot?
30/07/18	2b	Add code to make one-hot vectors for Y	Building y hangs at 39%
	1c interpolate		hansard_gathering/processed_hansard_data/1939-09-05/Oral Answers to Questions &#8212; Naval and Military Pensions and Grants..txt unable to interpolate due to NLTK bugs. TreeBankWordTokenizer tokenizer’s SpanTokenize does not work.	Rough-shod fix: remove all double-quotes from the file. Pending an NLTK issue: https://github.com/nltk/nltk/issues/1750
			NLTK acknowledges that the span tokenizer is still buggy at https://github.com/nltk/nltk/pull/2037
			Need to script this… Can replace double-quotes with single, seems to work
			If changing original data is sacrosanct, can always do a crawling character-window to try to do labelling
31/07/18			y vectors with one-hots take hours to create. I guess it’s all the sparsity. Looking into Digital Ocean droplets
01/08/18	2c create y		Traceback (most recent call last): / File "/Users/mralph/bbk/masters_project/masters_venv/bin/inv", line 11, in <module> / sys.exit(program.run()) / File "/Users/mralph/bbk/masters_project/masters_venv/lib/python3.6/site-packages/invoke/program.py", line 293, in run / self.execute() / File "/Users/mralph/bbk/masters_project/masters_venv/lib/python3.6/site-packages/invoke/program.py", line 414, in execute / executor.execute(*self.tasks) / File "/Users/mralph/bbk/masters_project/masters_venv/lib/python3.6/site-packages/invoke/executor.py", line 129, in execute / result = call.task(*args, **call.kwargs) / File "/Users/mralph/bbk/masters_project/masters_venv/lib/python3.6/site-packages/invoke/tasks.py", line 115, in __call__ / result = self.body(*args, **kwargs) / File "/Users/mralph/bbk/masters_project/tasks.py", line 169, in char_ner_create_y / model_integration.create_y(Config.sentence_max_length, dataset_name) / File "/Users/mralph/bbk/masters_project/keras_character_based_ner/src/matt/model_integration.py", line 102, in create_y / pickle_large_file(y_np, "keras_character_based_ner/src/y_np-{}.p".format(dataset_name)) / File "/Users/mralph/bbk/masters_project/keras_character_based_ner/src/matt/file_management.py", line 135, in pickle_large_file / bytes_out = pickle.dumps(data_structure) / OverflowError: cannot serialize a bytes object larger than 4 GiB	use pickle v4 protocol
02/08/18		Running model will take 80 hours, running on Digital Ocean droplet instead		DigitalOcean droplet
				Also take only the first 400000 sentences of each tensor in toy dataset, to create a quicker-to-run model
03/08/18			mini dataset needs to be wired into CHarBasedNERDataset	Subclass the CharBasedNERDataset and override its get_x_y so we don’t change the original source code too much
		Mini dataset ran through model	ImportError: `save_model` requires h5py.	Saved myself waiting 4 days for that!
			100 epochs	Subclass Config object	subclassing of the keras_character_based_ner project to make my contribution clear
		Minidataset used to predict a simple string, 'My name is Margaret Thatcher, and I greatly enjoy shopping at Tesco when I am in Birmingham!')	0s for everything, no named entities detected	To investigate	Disappointing, as a straight Interpolation would have recognised this out of the box. But we’re only using first 4000 sentences of toy dataset, and Margaret Thatcher did not appear in them.
	2c pickle model data	Got history object, tried to pickle	Cannot pickle Keras history objects, as their classes contain Lambdas which are not pickle-able	Instead, use the history object to create a graph straight away, and save that?
		History object pickled, need to graph	Can’t work out pyplot to graph png to file
	2c run model	Got access to BBK ubuntu server	Need to copy over tensors and kick off model	fix VPN, copy over all data	Server spec
05/08/2018 – 07/08/2018	2c run model		Model crashes: / 2018-08-05 07:28:40.266927: I tensorflow/core/platform/cpu_feature_guard.cc:141] Your CPU supports instructions that this TensorFlow binary was not compiled to use: AVX2 A / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/backend/tensorflow_backend.py", line 2478, in __call__ / out = K.gather(self.embeddings, inputs) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/backend/tensorflow_backend.py", line 1211, in gather / return tf.gather(reference, indices) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/ops/array_ops.py", line 2666, in gather / return gen_array_ops.gather_v2(params, indices, axis, name=name) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/ops/gen_array_ops.py", line 3141, in gather_v2 / "GatherV2", params=params, indices=indices, axis=axis, name=name) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/framework/op_def_library.py", line 787, in _apply_op_helper / op_def=op_def) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/framework/ops.py", line 3414, in create_op / op_def=op_def) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/framework/ops.py", line 1740, in __init__ / self._traceback = self._graph._extract_stack() # pylint: disable=protected-access / InvalidArgumentError (see above for traceback): indices[29,189] = 161 is not in [0, 160) / [[Node: embedding_1/GatherV2 = GatherV2[Taxis=DT_INT32, Tindices=DT_INT32, Tparams=DT_FLOAT, _class=["loc:@training/Adam/cond/Switch_5"], _device="/job:localhost/ / replica:0/task:0/device:CPU:0"](embedding_1/embeddings/read, embedding_1/Cast, metrics/non_null_label_accuracy/GatherV2_1/axis)]] **self.session_kwargs) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 900, in run / run_metadata_ptr) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 1135, in _run / feed_dict_tensor, options, run_metadata) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 1316, in _do_run / run_metadata) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 1335, in _do_call / raise type(e)(node_def, op, message) / tensorflow.python.framework.errors_impl.InvalidArgumentError: indices[29,189] = 161 is not in [0, 160) / [[Node: embedding_1/GatherV2 = GatherV2[Taxis=DT_INT32, Tindices=DT_INT32, Tparams=DT_FLOAT, _class=["loc:@training/Adam/cond/Switch_5"], _device="/job:localhost/ / replica:0/task:0/device:CPU:0"](embedding_1/embeddings/read, embedding_1/Cast, metrics/non_null_label_accuracy/GatherV2_1/axis)]] / Caused by op 'embedding_1/GatherV2', defined at: / File "/home/mralph02/.local/bin/inv", line 11, in <module> / sys.exit(program.run()) / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/program.py", line 293, in run / self.execute() / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/program.py", line 414, in execute / executor.execute(*self.tasks) / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/executor.py", line 129, in execute / result = call.task(*args, **call.kwargs) / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/tasks.py", line 115, in __call__ / result = self.body(*args, **kwargs) / File "/home/mralph02/masters_project/tasks.py", line 206, in model_train_toy / train.toy_dataset_fit() / File "/home/mralph02/masters_project/keras_character_based_ner/src/matt/train.py", line 42, in toy_dataset_fit / model = SavedCharacterBasedLSTMModel(config, dataset) / File "/home/mralph02/masters_project/keras_character_based_ner/src/matt/train.py", line 10, in __init__ / super().__init__(config, dataset) / File "/home/mralph02/masters_project/keras_character_based_ner/src/model.py", line 18, in __init__ / self.model = self.get_model() / File "/home/mralph02/masters_project/keras_character_based_ner/src/model.py", line 29, in get_model / mask_zero=True)) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/models.py", line 467, in add / layer(x) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/engine/topology.py", line 619, in __call__ / output = self.call(inputs, **kwargs) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/layers/embeddings.py", line 138, in call / VX512F FMA / 129920/2323449 [>.............................] - ETA: 54:33:05 - loss: 0.1656 - categorical_accuracy: 0.9521 - non_null_label_accuracy: 0.3744Traceback (most recent call / last): / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 1322, in _do_call / return fn(*args) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 1307, in _run_fn / options, feed_dict, fetch_list, target_list, run_metadata) / File "/home/mralph02/.local/lib/python3.5/site-packages/tensorflow/python/client/session.py", line 1409, in _call_tf_sessionrun / run_metadata) / tensorflow.python.framework.errors_impl.InvalidArgumentError: indices[29,189] = 161 is not in [0, 160) / [[Node: embedding_1/GatherV2 = GatherV2[Taxis=DT_INT32, Tindices=DT_INT32, Tparams=DT_FLOAT, _class=["loc:@training/Adam/cond/Switch_5"], _device="/job:localhost/ / replica:0/task:0/device:CPU:0"](embedding_1/embeddings/read, embedding_1/Cast, metrics/non_null_label_accuracy/GatherV2_1/axis)]] / During handling of the above exception, another exception occurred: / Traceback (most recent call last): / File "/home/mralph02/.local/bin/inv", line 11, in <module> / sys.exit(program.run()) / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/program.py", line 293, in run / self.execute() / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/program.py", line 414, in execute / executor.execute(*self.tasks) / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/executor.py", line 129, in execute / result = call.task(*args, **call.kwargs) / File "/home/mralph02/.local/lib/python3.5/site-packages/invoke/tasks.py", line 115, in __call__ / result = self.body(*args, **kwargs) / File "/home/mralph02/masters_project/tasks.py", line 206, in model_train_toy / train.toy_dataset_fit() / File "/home/mralph02/masters_project/keras_character_based_ner/src/matt/train.py", line 44, in toy_dataset_fit / history = model.fit() / File "/home/mralph02/masters_project/keras_character_based_ner/src/model.py", line 69, in fit / callbacks=[early_stopping, checkpointer]) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/models.py", line 963, in fit / validation_steps=validation_steps) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/engine/training.py", line 1705, in fit / validation_steps=validation_steps) / File "/home/mralph02/.local/lib/python3.5/site-packages/keras/engine/training.py", line 1235, in _fit_loop / outs = f(ins_batch)	Alphabet inconsistency? When the model starts, it calls get_alphabet_from_texts(texts) to get an alphabet, but when it numerifies, it uses an alphabet pickled to disk, to do the numerifying. Pickled alphabet is created using alphabet-sample and so is the model – but maybe the pickle is stale now? Regenerated the alphabet, the new one is completely different – better rerun the whole create-x and create-y, then the minification. X train test dev DONE. Y train test dev DONE. Minify.
07/08/18	2c graphing of training	Learn matlotplib pyplot API
		What is non null label accuracy?
09/08/18	2b fit model	Complete training	Long delay at end of each epoch to validate data	Just wait
			NaN for validation at end of each epoch	TODO try fixes here https://github.com/keras-team/keras/issues/2134
	2b use model to predict on a hansard	Create Inv task to test this
11/08/18	2b train			model completed training	(masters_venv) mralph02@venus:~/masters_project$ inv model-train-toy / Using TensorFlow backend. / Listing Hansard debate files from dataset alphabet-sample... / Train on 2323449 samples, validate on 1233718 samples / Epoch 1/4 / 2018-08-07 20:14:55.194687: I tensorflow/core/platform/cpu_feature_guard.cc:141] Your CPU supports instructions that this TensorFlow binary was not compiled to use: AVX2 AVX512F FMA / 2323424/2323449 [============================>.] - ETA: 1s - loss: 0.0990 - categorical_accuracy: 0.9701 - non_null_label_accuracy: 0.5915 / 2323449/2323449 [==============================] - 145730s 63ms/step - loss: 0.0990 - categorical_accuracy: 0.9701 - non_null_label_accuracy: 0.5915 - val_loss: nan - val_categorical_accuracy: nan - val_non_null_label_accuracy: nan / Epoch 00001: val_loss did not improve / Epoch 2/4 / 2323449/2323449 [==============================] - 142537s 61ms/step - loss: 0.0884 - categorical_accuracy: 0.9732 - non_null_label_accuracy: 0.6357 - val_loss: nan - val_categorical_accuracy: nan - val_non_null_label_accuracy: nan / Epoch 00002: val_loss did not improve / Epoch 00002: early stopping / 1157309/1157309 [==============================] - 17682s 15ms/step / [('M', '0'), ('y', '0'), (' ', '0'), ('n', '0'), ('a', '0'), ('m', '0'), ('e', '0'), (' ', '0'), ('i', '0'), ('s', '0'), (' ', '0'), ('M', 3), ('a', 3), ('r', 3), ('g', 3), ('a', 3), ('r', 3), ('e', 3), ('t', 3), (' ', 3), ('T', 3), ('h', 3), ('a', 3), ('t', 3), ('c', 3), ('h', 3), ('e', 3), ('r', 3), (',', '0'), (' ', '0'), ('a', '0'), ('n', '0'), ('d', '0'), (' ', '0'), ('I', '0'), (' ', '0'), ('g', '0'), ('r', '0'), ('e', '0'), ('a', '0'), ('t', '0'), ('l', '0'), ('y', '0'), (' ', '0'), ('e', '0'), ('n', '0'), ('j', '0'), ('o', '0'), ('y', '0'), (' ', '0'), ('s', '0'), ('h', '0'), ('o', '0'), ('p', '0'), ('p', '0'), ('i', '0'), ('n', '0'), ('g', '0'), (' ', '0'), ('a', '0'), ('t', '0'), (' ', '0'), ('T', '0'), ('e', '0'), ('s', '0'), ('c', '0'), ('o', '0'), (' ', '0'), ('w', '0'), ('h', '0'), ('e', '0'), ('n', '0'), (' ', '0'), ('I', '0'), (' ', '0'), ('a', '0'), ('m', '0'), (' ', '0'), ('i', '0'), ('n', '0'), (' ', '0'), ('B', 1), ('i', 1), ('r', 1), ('m', 1), ('i', 1), ('n', 1), ('g', 1), ('h', 1), ('a', 1), ('m', 1), ('!', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0'), ('<PAD>', '0')]
			Model stopped at epoch 2 due to validation loss being NaN	Try to find out why it’s NaN, or just pull out EarlyStopping
				check all numpy vectors for NaNs	Checked all to see if they contained NaNs… none do. None is inf either
			Remove EarlyStopping and keep training	Refactored to use CharBasedLSTMModel even for model loaded off disk, so we can resume training – and with no EarlyStopping	Had to remove EarlyStopping as it only gave 2 Epochs of training. Doing a further 5 on it now…
			circular import dependencies conflicting..	put all in one file
			Fix NaN in validation	Email Dell, clipnorm on gradients
17/08/18	6 evaluation	Get cross-validation code and general model-evaluation code ready		Wrote cross-validation code ready for when model is done training
	5 GUI	Write a mock GUI as a back-up plan		Wrote simple flask app to see debates in browser
	2b	Make model predict	Model has hugely overfitted	Gather evaluation of ToyV1 & history graphs if available
				Kick off ToyV2 training with small dataset (using create-x and create-y methods) and solve NaN Validation problem
18/08/18	5 GUI	Ajax call to predict_str
19/0818	2b model	ToyV2 has validation scores! Still improving		Had run for 3 epochs, started running for 3 more	Epoch 1/3 / 2018-08-18 11:55:45.743209: I tensorflow/core/platform/cpu_feature_guard.cc:141] Your CPU supports instructions that this TensorFlow binary was not compiled to use: AVX2 / AVX512F FMA / 500000/500000 [==============================] - 29095s 58ms/step - loss: 0.1228 - categorical_accuracy: 0.9624 - non_null_label_accuracy: 0.5163 - val_loss: 0.2072 - val / _categorical_accuracy: 0.9242 - val_non_null_label_accuracy: 0.4389 / Epoch 00001: val_loss improved from inf to 0.20722, saving model to /tmp/model.weights.hdf5 / Epoch 2/3 / 500000/500000 [==============================] - 29182s 58ms/step - loss: 0.0978 - categorical_accuracy: 0.9694 - non_null_label_accuracy: 0.5903 - val_loss: 0.1930 - val / _categorical_accuracy: 0.9316 - val_non_null_label_accuracy: 0.4653 / Epoch 00002: val_loss improved from 0.20722 to 0.19298, saving model to /tmp/model.weights.hdf5 / Epoch 3/3 / 500000/500000 [==============================] - 29249s 58ms/step - loss: 0.0940 - categorical_accuracy: 0.9709 - non_null_label_accuracy: 0.6207 - val_loss: 0.1874 - val / _categorical_accuracy: 0.9375 - val_non_null_label_accuracy: 0.5448