## Plan
ID	Work package	Target date	Risks / mitigations
1	a. Sourcing and aggregation of data sources for Named Entities of companies, people and places. / b. Download all Hansards as one dataset / c. Preparation of Hansard documents with NEs interpolated into the document using the NE lists aggregated above.	End April 2018	Data may not be available, or may be in unworkable formats. Use other/less data.
2	Perform manual validation of above Hansard documents to complete semi-automatic labelled data. / Construction of NER learning model BLSTM; integration with and modification of https://github.com/0xnurl/keras_character_based_ner implementation.	End May 2018	Model may not perform the task
3	Familiarisation with Samtla SLM. Conversion of Hansard into correct format, and loading of Hansard data into Samtla.	Mid June 2018	Samtla SLM API may not be complete. Mitigation is for Dr Martyn Harris to load the corpus into the SML manually.
4	Familiarisation with Samtla back-end (Python Django) and integration of NER processing with departmental server.	End June 2018	Integration may not be possible due to unforeseen dependencies.
5	Familiarisation with Samtla front-end (Javascript jQuery) and integration of NER visualization.	End July 2018	Integration may not be possible due to unforeseen dependencies.
6	Evaluation of Samtla Char-NER system using k-fold cross-validation techniques. (train on only part of data)	End August 2018	Fall back to simpler evaluation methods; as a last-resort, crowd-source evaluation of Hansards enriched with NE data.
7	Finalise write-up into report	Before 17th Sept 2018

## Work Log
Date	WorkPackage	Progress	Issues	Resolutions
26/04/18	1a sourcing NEs	Worked on Kaggle NYC baby names	Names can be FN-LN or just FN. I guess we want to be able to detect both, as both occur in speech	Manually split all names up into FN, LN as well? Makes recognition more likely…
		DBPedia SPARQL got list of people	1.They’re in Unicode	To check with Martyn Harris
			2. They have profession names etc in brackets	Used foaf:name instead, fixed
			3. Tony Blair is a Person, but then so is Shadow_Cabinet_of_Tony_Blair	Post-processing validation?

		Post-processing of names	4.Duplicates not a problem – e.g. Ralph Allwood and Ralph Allwood, MBE – could both appear in a text. Entries like below ARE A problem:	TODO: remove start ad end brackets and quotes (without messing up unicode)
			(15 July 1914 – 8 November 1927)
			(1833-1905)

			5. Lots of Chinese, Russian and Arabic names – no principled reason to remove them, but it’s unlikely they would appear natively in Hansard
			6. biography-center.com no longer has names in easy parseable format	Scrap it – we have enough names from DBPedia
		Processed CONLL data	Reuters dataset not included
		SPARQL got list of companies	no issues
		SPARQL got list of places	no issues
07/07/18	Examine Keras	Correct typos
09/07/18	1a sourcing NEs	Remove double quotes from outputs, sanitise output dirs
	1b sourcing Hansards	Wrote multi-Hansard-Downloader using TWFY API which starts in 1919	serial download v slow before finding concurrent.futures – put comparative timings in report? Tried multiprocessing and infinite num of threads too
11/07/18	1b sourcing hansards	Today I found another API source for Hansard: https://api.parliament.uk/historic-hansard/	My scripts are written for https://www.theyworkforyou.com/api/, but this only goes back to 1919.
	1b preprocessing of Hansards	Downloaded raw hansards	They need HTML chars escaping in xml files	lxml etree
		Processed hansards	They need all markup lang tags removing	lxml etree
			bleach.clean failed to remove nested markup tags	lxml etree
			Used lxml etree which successfully removed all tags. But now speaker names are not shown, as they are only nested in the XML tags.	TODO find a way to preserve speaker names in the future.
			lxml etree does not like Unicode strings.	Had to force-encode string as utf-8 and the etree parser as utf-8 to fix
		Try feeding Hansards into Keras model	Keras model is designed for max sent len of 200. If a debate is a sentence, max is 1.13m characters. We need to subdivide up the debates.	Add a new stage: file chunking. We ideally want to avoid chopping up an NE across 2 files…
			TextBlob struggles to segment accurately on sentence with ‘hon. Gentleman’.	TextBlob segmentation V SLOW, nltk was much faster
			NLTK still can’t cope with hon. Gentleman	Investigate https://stackoverflow.com/questions/34805790/how-to-avoid-nltks-sentence-tokenizer-spliting-on-abbreviations	Fixed using NLTK custom tokenizer
13/07/18	2 Integration with Keras	Try to integrate x with keras before solving interpolation (y) problem	Need to construct Numpy arrays with numerised alphabet. To do this, I need to get union of all characters used in the whole dataset	Create get_some_alphabet which just uses texts from the 1940s to construct alphabet. Hopefully we won’t have too many more characters since then.
				Use none-chunked Hansards as we still have same characters in them and it’s MUCH quicker.
				Save out alphabet object using Pickle
13/07/18	1c NE interpolation	Trying to interpolate such that words are turned into e.g. OOOO, but all whitespace and punctuation is preserved	word_tokenizer in NLTK only returns a list of words. To get spans of word start/ends, need to use a span_tokenizer which is not included in NLTK default tokenizer

				≈