## Plan
ID	Work package	Target date	Risks / mitigations
1	a. Sourcing and aggregation of data sources for Named Entities of companies, people and places. / b. Download all Hansards as one dataset / c. Preparation of Hansard documents with NEs interpolated into the document using the NE lists aggregated above.	End April 2018	Data may not be available, or may be in unworkable formats. Use other/less data.
2	a. Perform manual validation of above Hansard documents to complete semi-automatic labelled data. / b. Construction of NER learning model BLSTM by constructing tensors; integration with and modification of https://github.com/0xnurl/keras_character_based_ner implementation.	End May 2018	Model may not perform the task
3	Familiarisation with Samtla SLM. Conversion of Hansard into correct format, and loading of Hansard data into Samtla.	Mid June 2018	Samtla SLM API may not be complete. Mitigation is for Dr Martyn Harris to load the corpus into the SML manually.
4	Familiarisation with Samtla back-end (Python Django) and integration of NER processing with departmental server.	End June 2018	Integration may not be possible due to unforeseen dependencies.
5	Familiarisation with Samtla front-end (Javascript jQuery) and integration of NER visualization.	End July 2018	Integration may not be possible due to unforeseen dependencies.
6	Evaluation of Samtla Char-NER system using k-fold cross-validation techniques. (train on only part of data)	End August 2018	Fall back to simpler evaluation methods; as a last-resort, crowd-source evaluation of Hansards enriched with NE data.
7	Finalise write-up into report	Before 17th Sept 2018

## Work Log
Date	WorkPackage	Progress	Issues	Resolutions	Extra content for Report
26/04/18	1a sourcing NEs	Worked on Kaggle NYC baby names	Names can be FN-LN or just FN. I guess we want to be able to detect both, as both occur in speech	Manually split all names up into FN, LN as well? Makes recognition more likely…	benefits of the pipeline approach – can iteratively improve each stage and only re-run downstream jobs
		DBPedia SPARQL got list of people	1.They’re in Unicode	To check with Martyn Harris
			2. They have profession names etc in brackets	Used foaf:name instead, fixed
			3. Tony Blair is a Person, but then so is Shadow_Cabinet_of_Tony_Blair	Post-processing validation?

		Post-processing of names	4.Duplicates not a problem – e.g. Ralph Allwood and Ralph Allwood, MBE – could both appear in a text. Entries like below ARE A problem:	TODO: remove start ad end brackets and quotes (without messing up unicode)
			(15 July 1914 – 8 November 1927)
			(1833-1905)

			5. Lots of Chinese, Russian and Arabic names – no principled reason to remove them, but it’s unlikely they would appear natively in Hansard
			6. biography-center.com no longer has names in easy parseable format	Scrap it – we have enough names from DBPedia
		Processed CONLL data	Reuters dataset not included
		SPARQL got list of companies	no issues
		SPARQL got list of places	no issues
07/07/18	Examine Keras	Correct typos
09/07/18	1a sourcing NEs	Remove double quotes from outputs, sanitise output dirs
	1b sourcing Hansards	Wrote multi-Hansard-Downloader using TWFY API which starts in 1919	serial download v slow before finding concurrent.futures – put comparative timings in report? Tried multiprocessing and infinite num of threads too
11/07/18	1b sourcing hansards	Today I found another API source for Hansard: https://api.parliament.uk/historic-hansard/	My scripts are written for https://www.theyworkforyou.com/api/, but this only goes back to 1919.
	1b preprocessing of Hansards	Downloaded raw hansards	They need HTML chars escaping in xml files	lxml etree
		Processed hansards	They need all markup lang tags removing	lxml etree
			bleach.clean failed to remove nested markup tags	lxml etree
			Used lxml etree which successfully removed all tags. But now speaker names are not shown, as they are only nested in the XML tags.	TODO find a way to preserve speaker names in the future.
			lxml etree does not like Unicode strings.	Had to force-encode string as utf-8 and the etree parser as utf-8 to fix
	2b	Try feeding Hansards into Keras model	Keras model is designed for max sent len of 200. If a debate is a sentence, max is 1.13m characters. We need to subdivide up the debates.	Add a new stage: file chunking. We ideally want to avoid chopping up an NE across 2 files…
			TextBlob struggles to segment accurately on sentence with ‘hon. Gentleman’.	TextBlob segmentation V SLOW, nltk was much faster
			NLTK still can’t cope with hon. Gentleman	Investigate https://stackoverflow.com/questions/34805790/how-to-avoid-nltks-sentence-tokenizer-spliting-on-abbreviations	Fixed using NLTK custom tokenizer
13/07/18	2b Integration with Keras	Try to integrate x with keras before solving interpolation (y) problem	Need to construct Numpy arrays with numerised alphabet. To do this, I need to get union of all characters used in the whole dataset	Create get_some_alphabet which just uses texts from the 1940s to construct alphabet. Hopefully we won’t have too many more characters since then.
				Use none-chunked Hansards as we still have same characters in them and it’s MUCH quicker.
				Save out alphabet object using Pickle
13/07/18	1c NE interpolation	Trying to interpolate such that words are turned into e.g. OOOO, but all whitespace and punctuation is preserved	word_tokenizer in NLTK only returns a list of words. To get spans of word start/ends, need to use a span_tokenizer which is not included in NLTK default tokenizer
		There’s a tension between work that’s easy to reason with (having each stage on disk), and work that’s efficient and processes quickly enough (skipping stages, delete as going along etc)
		String type immutable in Python	Trying inv hansard-interpolate-one hansard_gathering/chunked_hansard_data/1949-07-14/Oral\ Answers\ to\ Questions\ \&\#8212\;\ Electoral\ Register-chunk-388.txt cannot modify string. Either change to use concat, or a ctype as per https://stackoverflow.com/questions/10572624/mutable-strings-in-python	≈
17/07/18		Used string concat which works fine. Now can’t find any NEs as multi-word phrases are ignored by tokenizer.	Need to try multiple-word lookups in the NE files	word tokenizer in groups, or sliding n-grams?
18/07/18	1c NE interpolation	Fix tokenizing for interpolation – try NLTK ngrams		Keep working on hansard_gathering/chunked_hansard_data/1949-07-14/Oral Answers to Questions &#8212; Electoral Register-chunk-388.txt
				Solution was to use sliding windows over text spans, then for each window, try all suffixes from longest to shortest, in all the NE files	Examining I do recall that / Examining I do recall / Examining I do / Examining I / Examining do recall that Margaret / Examining do recall that / Examining do recall / Examining do / Examining recall that Margaret Thatcher / Examining recall that Margaret / Examining recall that / Examining recall / Examining that Margaret Thatcher was / Examining that Margaret Thatcher / Examining that Margaret / Examining that / Examining Margaret Thatcher was good / Examining Margaret Thatcher was / Examining Margaret Thatcher
	1b chunking	Need to process Hansards but have no disk	Not enough disk space on MAC	Back up raw hansards in tgz, then make processing algo delete raw hansards as it goes
		Interpolation throws up weird errors:
	1a	I have searched the International Monetary Fund rules, and I cannot find under which rule this is done.	I is an Org, The is a location, ‘.’ is a location…	Manual correction – remove ‘I’ from companies list ALL.txt. This came from DBPedia… Removed ‘.’ from locations and ‘the’
		2000000000000000111022222222222222222222222222200000010111020000000000000000000000000000000000000000001		Better resolution is to throw away words < 4 chars at processing stage, doing this now
	1b chunking	Starting chunk all	Chunking is very slow	Make chunking resumable by allowing date to be specified
		Interpolation works!		mattlap:~/bbk/masters_project mralph$ cat hansard_gathering/chunked_hansard_data/1929-12-23/Egypt.-chunk-1051.txt / It is sometimes said that it would be impossible, but I know there are experts who hold, on the contrary, that it would be a very strong position, and, indeed, actually stronger than a position based upon Cairo and Alexandria if Egypt were in revolt against our action.% mattlap:~/bbk/masters_project mralph$ cat hansard_gathering/interpolated_hansard_data/1929-12-23/Egypt.-chunk-1051.txt / 00000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000001111100000111111111100001111100000000000000000000000000000000000%
	2b Keras get x from texts	Need to translate chunked docs into numbered encodings	Don’t want to do padding in case sentence_maxlen changes	Decouple numerification from padding, do padding closer to keras-loading
		Cannot unpickle alphabet to encode debates into numbers	You can’t pickle in one module structure and unpickle in another. Have to wrap the keras char-based ner code into my module structure with __init__.py files
19/07/18	1c chunk	Run out of disk space	chunked sentences are too large	gzip in python
			Backup locations: raw on pen drive
			processed on dropbox
			Space blow out is caused by storing individual sentences in each file. Minimum file size is 4K – a lot of wasted space! Disk spin must have been limiting performance.	Get external drive and put different block size / filesystem on it	mattlap:~/bbk/masters_project/hansard_gathering/chunked_hansard_data/1965-07-22 mralph$ du -sh 'Security Commission (Report on Bossard and Allen Cases)-chunk-3511.txt.gz' / 4.0KSecurity Commission (Report on Bossard and Allen Cases)-chunk-3511.txt.gz / mattlap:~/bbk/masters_project/hansard_gathering/chunked_hansard_data/1965-07-22 mralph$ stat -f%z !$ / stat -f%z 'Security Commission (Report on Bossard and Allen Cases)-chunk-3511.txt.gz' / 218
				New idea: re-order pipeline so we interpolate directly from the processed data. Maybe we can chunk later, as we make sequences to feed into the model?
				Or maybe we chunk, but we just store the sentence offsets in their own file??
22/07/18	1c chunk	Method written to biew file with sentence chunking based on a separate chunk spans file
	1a	Improve NE data hygiene before interpolating all Hansards
23/07/18	1a sourcing NEs	Split out job so I can just post-process NEs without re-downloading from SparQL-wiki	need to refactor, lots of repetition
		can’t remove brackets from start and end of NEs	They’re not standard ASCII brackets, need to find ALL brackets in Unicode		166 ( Institut catholique de Lyon ) / 167 ( Kanakpak Khemara Ponnakar ) / 168 ( Kommunistische Partei Deutschlands ) / 169 ( Le bureau national d'examen dentaire du Canada ) / 170 ( Mǎ Lái Xī Yà Fó Xué Yuàn ) / 171 ( Nasionale Konserwatiewe Party van Suid-Afrika) / 172 ( PT Media Nusantara Citra Televisi Indonesia) / 173 ( Pusat Pemantauan dan Pendedahan Maklumat Kebangsaan )
		extraneous quotes, whitespace, asterisks
	2a interpolation	NLTK 3.2 has bug for span_tokenize if it contains multiple quotation types	file_path = 'hansard_gathering/processed_hansard_data/1919-08-04/Oral Answers to Questions &#8212; Railway Materials in War Area..txt' / with open(file_path) as f: / ...: text: str = f.read() / ...: interpolated_text: str = "0" * len(text) / from datetime import datetime / ...: from nltk.tokenize import TreebankWordTokenizer / ...: from nltk import ngrams / ...: from typing import List / ...: import concurrent.futures / ...: import glob / ...: import itertools / ...: import os / ...: / tokenizer = TreebankWordTokenizer() / text_span_ngrams = ngrams(tokenizer.span_tokenize(text), n, pad_right=True)	Upgrade to NLTK 3.3 https://github.com/nltk/nltk/pull/2060
			results in
			--------------------------------------------------------------------------- / ValueError Traceback (most recent call last) / ~/bbk/masters_project/masters_venv/lib/python3.6/site-packages/nltk/tokenize/util.py in align_tokens(tokens, sentence) / 253 try: / --> 254 start = sentence.index(token, point) / 255 except ValueError: / ValueError: substring not found / During handling of the above exception, another exception occurred: / ValueError Traceback (most recent call last) / <ipython-input-36-01430904daf3> in <module>() / ----> 1 tokenizer.span_tokenize(half_text) / ~/bbk/masters_project/masters_venv/lib/python3.6/site-packages/nltk/tokenize/treebank.py in span_tokenize(self, text) / 177 tokens = raw_tokens / 178 / --> 179 return align_tokens(tokens, text) / 180 / 181 / ~/bbk/masters_project/masters_venv/lib/python3.6/site-packages/nltk/tokenize/util.py in align_tokens(tokens, sentence) / 254 start = sentence.index(token, point) / 255 except ValueError: / --> 256 raise ValueError('substring "{}" not found in "{}"'.format(token, sentence)) / 257 point = start + len(token) / 258 offsets.append((start, point)) / ValueError: substring "passed." not found in "
	2a interpolation	Interpolated a whole debate	Overlaps – if The House has been successfully interpolated as a Place, House, which is a company, overwrites the labels for the second half, leaving a dangling ‘The’	Change algorithm so that it checks if the current span is in the middle of an already-NE’d span, and skips it if so	def overlaps(ngram_span_window, recentest_match_end: int): / """ / See if the current span window already has a matched NE ending in it. / :param ngram_span_window: e.g.((0, 1), (2, 6), (7, 15), (16, 19)) / Note that because we pad_right, later elements in the tuple might be None, e.g.: / ((98, 102), (102, 103), None, None) / :param recentest_match_end: / :return: True if there would be an overlap / """ / ngrams = [x for x in ngram_span_window if x is not None] / return ngram_span_window[-1][-1] <= recentest_match_end
24/07/18	2a	Fixed overlap bug	Interpolation is too slow. It may be the python ‘in’ membership check	Replace list with set?	TODO compare list with set – speed improves hugely!!! From about 20 minutes to 5 seconds. How implemented?
			Still random places – e.g. ‘and the’ as a place, in SPARQL data	Remove all lines comprised of stop words?	A Dirty Data section?
25/07/18	2a interpolating	Fix datetime bug where month ignored	Was using %M not %m in datetime filter	corrected
	1a NE gathering	Need to remove stop-words from NE list	e.g. remove ‘and the’ as a place
		tech debt clean up	Allow all tasks to be invoked from tasks.py without shell
			Make all type checks pass
	2b preparation of x tensor	Need to determine some datasets	The model requires train, dev and test. Relative sizes? Can’t use date ranges or alphabetical division as that would bias the datasets. Need to hash all the data into 3 buckets of unequal sizes, such that it can be easily repeated in future.	Use last 2 parts of file path as entry into a hashing algorithm, e.g. “1972-07-20/Orders of the Day &#8212; Clause 211.txt”. Build up a list of which filenames are in which data set	Buckets have equal numbers of files: / Mattlap:~/bbk/masters_project/hansard_gathering/data_buckets mralph$ wc -l * / 8360 0.txt / 8414 1.txt / 8228 2.txt / 8322 3.txt / 8289 4.txt / 8071 5.txt / 8356 6.txt / 8419 7.txt / 66459 total
			accidentally overwrote hansard_gathering/processed_hansard_data/1948-07-13/Oral Answers to Questions &#8212; Prisoners of War (Repatriation).txt	Restore from backup
			Numerification is too slow. Doing lots of re-assignment of strings	Instead make a list of numbers, then join it as a last step	show change in 17d4716aadb8389d9aaf10a7a0d543e7ceda196e to numerify.py
	1c interpolation	Interpolation is the new bottleneck	We are re-assigning to string a lot to build the interpolated string	Can we make this faster by replacing the string re-assignment operations with a List, and stringify at the end? Done. Faster?
	2b tensor construction	Counted up total number of sentences (batch_size) for each dataset		As hoped for, train is half the dataset and dev/test are both half of it in size, more or less	mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat ALL_total_sentences_num / 182582013 / mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat train_total_sentences_num / 91294439 / mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat dev_total_sentences_num / 44985341 / mattlap:~/bbk/masters_project/hansard_gathering/processed_hansard_data mralph$ cat test_total_sentences_num / 46295292
27/08/18	2b tensor construction	It’s far too slow! Doing 0.01% takes about 20 minutes	Won’t have time to finish	Rehash across 320 buckets, then just try 1 bucket first to see if we can make a numpy array. Should go from 8000 debates per file to 200, 8 → 320 buckets is 40 times more